## Sheet1
Detail plan
Group 9 | Project Start: |  | 3/3/2024
| Project End: |  | 2024-09-04
| Projecct manager |  | Nguyễn Hoàng Sơn
Phase | Assigned to | TaskID | Task Name | Start Day | End Day
Planning
| Hoàng Phúc, An Thơ | 1 | Collect Requirement | 2024-03-03 | 2024-04-03
| Hữu Vinh, An Thơ | 2 | Implement Usecase | 2024-05-03 | 2024-06-03
|  | 3 | Implement Model Diagram
| Hữu Vinh | 3.1 | Sequence Diagram | 2024-07-03 | 2024-10-03
| Hữu Vinh | 3.2 | Activity Diagram | 2024-07-03 | 2024-10-03
| Hữu Vinh | 3.3 | State Diagram | 2024-07-03 | 2024-10-03
| Hữu Vinh | 3.4 | Class Diagram | 2024-07-03 | 2024-10-03
| Hữu Vinh | 4 | ERD | 2024-11-03 | 2024-12-03
| Hữu Vinh | 5 | Business rules | 2024-11-03 | 2024-12-03
| Hữu Vinh, Hoàng Sơn | 6 | Vision and Scope | 2024-11-03 | 2024-12-03
| Hữu Vinh | 7 | Context diagram | 2024-11-03 | 2024-12-03
| Hữu Vinh, An Thơ | 8 | Implement SRS document | 13/3/2024 | 15/3/2024
| An Thơ, Hữu Vinh | 9 | SDD | 15/3/2024 | 16/3/2024
| Hoàng Sơn | 10 | Design GUI
| Hoàng Sơn | 10.1 | Design for Admission management | 2024-11-03 | 15/3/2024
| Hoàng Sơn | 10.2 | Design for Book Mangager | 2024-11-03 | 15/3/2024
| Hoàng Sơn | 10.3 | Design for Making Export,Import Report | 2024-11-03 | 15/3/2024
| Hoàng Sơn | 10.4 | Design for Distributor, Publisher Manager | 2024-11-03 | 15/3/2024
| Hoàng Sơn | 10.5 | Design for Revenue Statistic | 2024-11-03 | 15/3/2024
Coding |  | 11 | develop for BookStore Management
| Hoàng Sơn | 11.1 | develop Admisstiton Registraion | 15/3/2024 | 18/3/2024
| Hoàng Sơn | 11.2 | develop Book Mangager | 15/3/2024 | 18/3/2024
| Hoàng Sơn | 11.3 | develop Distributor, Publisher Manager | 15/3/2024 | 18/3/2024
| Hoàng Sơn | 11.4 | develop Revenue Statistic | 15/3/2024 | 18/3/2024
| Hoàng Sơn | 11.5 | develop Making Export,Import Report | 18/3/2024 | 18/3/2024
| Hoàng Sơn | 11.6 | develop Making Export,Import Report print | 15/3/2024 | 18/3/2024
| Hoàng Sơn | 11.7 | develop import Statistic from distributor | 15/3/2024 | 18/3/2024
Testing |  | 14 | implement Exam management
| Hoàng Sơn | 14.1 | implement Admisstiton Registraion
| Hoàng Sơn | 14.2 | implement Book Mangager | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 14.3 | implement Distributor, Publisher Manager | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 14.4 | implement Revenue Statistic | 2024-01-04 | 2024-03-04
|  | 14.5 | implement Making Export,Import Report | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 14.6 | implement Making Export,Import Report print | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 14.7 | implement import Statistic from distributor | 2024-01-04 | 2024-03-04
|  | 15 | Build test plans | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 15.1 | Design test case for account registration | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 15.2 | Design test case for login | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 15.3 | Design test case for Book management (Create,edit,delete) | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 15.4 | Design test case for Distributor, Publisher management (Create,edit,delete) | 2024-01-04 | 2024-03-04
|  | 15.5 | Design test case for Revenue Statistic | 2024-01-04 | 2024-03-04
| Hoàng Sơn | 15.6 | Design test case Making Export,Import Report | 2024-04-04 | 2024-07-04
| Hoàng Sơn | 15.7 | Design test case for import Statistic from distributor | 2024-04-04 | 2024-07-04
| Hoàng Sơn | 16 | Implement test plans | 2024-04-04 | 2024-07-04
| Hoàng Sơn | 16.1 | implement test Admisstiton Registraion | 2024-04-04 | 2024-07-04
| Hoàng Sơn | 16.2 | implement test Book Mangager | 2024-04-04 | 2024-07-04
| Hoàng Sơn | 16.3 | implement test Distributor, Publisher Manager | 2024-04-04 | 2024-07-04
| Hoàng Sơn | 16.4 | implement test Revenue Statistic | 2024-04-04 | 2024-07-04
| Hoàng Sơn | 16.5 | implement test Making Export,Import Report | 2024-05-03 | 2024-05-03
| Hoàng Sơn | 16.6 | implement test Making Export,Import Report print
| Hoàng Sơn | 16.7 | implement test import Statistic from distributor
Error handling and source code optimization